## Sheet1
Risk ID | Date registered | Risk area | Risk description | Probability |  | Risk Level |  | Project impact | Proximity / Length of impact | Response strategy
1 | 2021-10-29 | Computer Crashing & Losing the data | My Laptop might crash for various reason. |  | / | / |  | This will impact the project as I would lose all progress made with this laptop. | N/A | going to libaaries or asking family members or in the future workplaces to borrow a laptop or device to continue the wotk | GitHub | https://github.com/Adammussa123
1 | 29/10.2021 | Schedule Risk | Not completing the project on time | / |  |  | / | Wrong time estimation Resources are not tracked properly. All resources like staff, systems, skills of individuals, etc. Failure to identify complex functionalities and time required to develop those functionalities. Unexpected project scope expansions. | 1 Weeks overall project sprint | On agile projects the team is heavily involved in planning and estimating through past experiience. Next time I need to focus solely on the task at hand. | Project Name: | QA-Project1
2 | 2021-10-29 | Git Merge Conflicts | I could have a merge conflicts or overwrite by merging incorrectly. | / |  |  | / | This could impact the project majorly as I would have to start from where the overwrite took place. I would also need to resolve a conflict merge issue | A day / 2 |  | Project Description:
3 | 2021-10-29 | Application crashing | Main project application crashing due to issues caused by deleing files or removing vital code |  | / |  | / | This can really effect the project as small code with issues can lead to the whole program not working | A day / 2 | Build in small steps, this will allow me to correct myself when I need to. I'd also know when or what is causing the issue as I will be building in increments | Project Owner: | Adam Mussa
4
5 | [10 empty] | Risk Level | Colour
6 | [10 empty] | Low
7 | [10 empty] | Medium
8 | [10 empty] | High
9
10 | [10 empty] | Medium
11 | [10 empty] | High
12
13
14
15
16
17
18